## Sheet1
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Game Rules | Karsen | 1 | 2020-03-05 | 100 | 2020-03-05 | 1
Functional Requirements | Stella | 1 | 2020-03-31 | 100 | 2020-03-31 | 1.5
Project Plan Week 1 | Alex | 1 | 2020-04-03 | 100 | 2020-04-03 | 1
Preliminary Class Design | Stella | 1.5 | 2020-04-07 | 100 | 2020-04-06 | 1.5
User Experience (UX) Mockup | Alex | 2 | 2020-04-07 | 100 | 2020-04-06 | 1.5
Project Plan Week 2 | Stella | 0.5 | 2020-04-10 | 0
System Test Plan | Leon | 2 | 2020-04-14 | 0
Card Class Code | Karsen | 2 | 2020-04-16 | 100 | 2020-04-01 | 1.5
Project Plan Week 3 | Leon | 0.5 | 2020-04-17 | 0
Hand Class Code | Karsen | 2 | 2020-04-18 | 100 | 2020-04-03 | 2
Main Class Code | Alex | 2.5 | 2020-04-20 | 50
GUI Card Graphics | Stella | 1 | 2020-04-20 | 15
Gui Main Code | Leon | 2.5 | 2020-04-22 | 0
Gui Options Screen | Stella | 1 | 2020-04-23 | 0
Create Test Cases | Leon | 1.5 | 2020-04-24 | 0
Project Plan Week 4 | Karsen | 0.5 | 2020-04-24
Test Code | Leon | 1 | 2020-04-25 | 0
Bugfix Code | Alex | 1.5 | 2020-04-26 | 0
Final Code Due | All |  | 2020-04-27
Presentation | Karsen | 3 | 2020-04-28 | 0
Practice Presentation | All | 0.5 | 2020-04-28 | 0
Final Report | Leon | 3 | 2020-05-01 | 0